## Slide 1
CB&PT Release Management Status
Executive Summary
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete | 
Oct 09, 2025
W | Core Banking - (Sep 21, 2025) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase: | REQ | DES | CON | DIT | SIT | UAT | PAT | INFRA | C/F | Scope: | 71 | 37 | Projects & MOPs | 8 | Regulatory
 | C | C | C | G | Y | Y | N | Y | Y |  |  | 34 | PRBs/INCs/Others | 4 | Financial
 | C | C | C | C | C | C | C | C | C |  |  |  |  |  | 
Apps: | 42 | 30 | CBPT |  | AIF, CAAP, CIBC R.Term, CLASS, COLT, DDGS, DDGS API, DM, DM (PEGA), ECM, EDTS, ENVOY, Excalibur, Excalibur API, Forms Management, IDP API, LCMS, LCMS API, Lending API, PCA/SAV, RPE, Remote Banking Batch, STB, TABS, W360 - FX, W360 - Non-Reg, W360 - RIF, W360 - RSP, W360 - TFSA, mMortgage |  |  |  |  |  |  |  |  |  | 
 |  | 12 | Non-CBPT |  | CASA, CIW, COINS (Host Facilities), COMPASS-AIM, ECIF, EDH, EDSF, GOW, Lending BI, MI Lending, PostEdge, eBanking |  |  |  |  |  |  |  |  |  | 
Comments: | Release has been implemented successfully. Warranty is complete. Production Issues: 41 [07 Scheduled, 34 Closed] |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R | Core Banking - (Nov 16, 2025) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase: | REQ | DES | CON | DIT | SIT | UAT | PAT | INFRA | C/F | Scope: | 61 | 32 | Projects & MOPs | 4 | Regulatory
 | C | C | C | G | Y | Y | N | Y | Y |  |  | 29 | PRBs/INCs/Others | 2 | Financial
 | G | G | G | G | Y | R | N | G | N |  |  |  |  |  | 
Apps: | 32 | 26 | CBPT |  | AMS, CAAP, CI, CLASS, COLT, DDGS, DDGS API, DM, DM (PEGA), ECM, EDTS, ENVOY, Excalibur, FX, FirstLine.com, Forms Management, IMDS, LAS, LCMS, Lending API, PCA/SAV, RPE, STB, TABS, Target, mMortgage |  |  |  |  |  |  |  |  |  | 
 |  | 06 | Non-CBPT |  | COMPASS-AIM, Client Messaging Alert Broker (CMAB), ECIF, EDH, SKP (Vendor), eBanking |  |  |  |  |  |  |  |  |  | 
Comments: | Release is Red as the impacted initiative listed below has testing delays caused by unresolved defects, SIT delays, and solution gaps, with key issues in data accuracy and formatting. UAT is dependent on E2E SIT which is delayed due to dependency on open defects from other teams (EDTS, GOW, Lending BI). Teams are prioritizing defect resolution and may re-baseline testing timelines if required. 3517¦Property Insurance Cancellation 4149¦NSOD Forms Update |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G | Core Banking - Feb 1, 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase: | REQ | DES | CON | DIT | SIT | UAT | PAT | INFRA | C/F | Scope: | 20 | 13 | Projects & MOPs |  | Regulatory
 | C | C | C | G | Y | Y | N | Y | Y |  |  | 7 | PRBs/INCs/Others |  | Financial
 | G | G | G | G | G | N | N | N | N |  |  |  |  |  | 
Apps: | 25 | 16 | CBPT |  | CAAP, CIBC R.Term, CLASS, DDGS, DM, ECM, Excalibur, Forms Management, KC, LCMS, Lending API, mMortgage, PostEdge, RPE, TABS, Target |  |  |  |  |  |  |  |  |  | 
 |  | 9 | Non-CBPT |  | Auth Hub, CCARS, CIW, eBanking, ECIF, EDSF, EPC, Fraud Analyst Engine (OLB), Lending BI |  |  |  |  |  |  |  |  |  | 
Comments: | Release is tracking Green. SIT execution is in progress. Detailed updates will be available as we approach the release. |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 2
CB&PT Release Management Status
Executive Summary
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete | 
Oct 9, 2025
G | Core Banking - Feb 1, 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Phase: | REQ | DES | CON | DIT | SIT | UAT | PAT | INFRA | C/F | Scope: | 20 | 13 | Projects & MOPs |  | Regulatory
 | C | C | C | G | Y | Y | N | Y | Y |  |  | 7 | PRBs/INCs/Others |  | Financial
 | G | G | G | G | G | N | N | N | N |  |  |  |  |  | 
Apps: | 25 | 16 | CBPT |  | CAAP, CIBC R.Term, CLASS, DDGS, DM, ECM, Excalibur, Forms Management, KC, LCMS, Lending API, mMortgage, PostEdge, RPE, TABS, Target |  |  |  |  |  |  |  |  |  | 
 |  | 9 | Non-CBPT |  | Auth Hub, CCARS, CIW, eBanking, ECIF, EDSF, EPC, Fraud Analyst Engine (OLB), Lending BI |  |  |  |  |  |  |  |  |  | 
Comments: | Release is tracking Green. SIT execution is in progress. Detailed updates will be available as we approach the release. |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 3
2026 Core Banking Release Calendar
Proposed Combined Releases
Summary:
Lending & Deposit Releases are combined in planning to simplify co-ordination and overhead in supporting release activities
Note:
Dates are subject to potential 2-week shift, dependent upon COINS/CLASS/GDF scope requirements necessitating a 2-week deployment stagger.
  This situation is rare, and will be handled ad-hoc as requirements come in.
  Given enough time, COINS Release can still be planned 2-weeks in advance of these dates, leaving no impact to Lending-side changes
2026 Freezes:
RRSP and Holiday Freeze have reduced in length, by removing first week from each.
Informal freeze imposed annually in last 2 weeks of June for Lending pipeline to support high volume funding season.
Freeze | Dates
RRSP Freeze | Feb 16 00:01 - Mar 2 23:59
Funding Freeze (Informal) | Jun 15 00:01 - Jun 30 23:59
Black Friday / Cyber Monday Freeze | Nov 27 00:01 - Nov 30 23:59
Holiday Freeze | Dec 14 00:01 - Jan 1 23:59
CBPT Core Banking Release Calendar 2026 | 
Release | Implementation Date
Core Banking 26.2 | February 1, 2026
Core Banking 26.3 | April 19, 2026
Core Banking 26.4 | July 5, 2026
Core Banking 26.5 | September 20, 2026
Core Banking 27.1 | November 15, 2026
AMS 2026 Release | December 6, 2026

## Slide 4: Apr Rel - Overview
RELEASE RECAP
PROD ISSUE BY INTAKE DISTRIBUTION & RCA
47
Release Items
24
CBPT Apps
6
External Apps
Key Initiatives
2616 | RDD (Renewal Due Diligence)
2646 | HPP MA Refinance
2682 | Mortgage Insurance Affordability
2921 | LCMS Routing for RESL
2800 | IDP (Intelligent Document Processing)
3081 | Insurer Enhancements and Priority Changes (Hopper 1)
3273 | Renewal Letter for Canadian Mortgage Charter
3843 / 3686 | RESL Pod Phase 2
4133 | What If Calculator
PRB0056242 | mMTG | Angular JS upgrade
Chart: 
| PRB Angular JS Upgrade | LCMS Routing | Hopper 1 | HPP MA Refi | Renewal Letter for Canadian Mrtg Charter | RESL POD Ph 2 | RDD | WIC | MIA
High | 1 | 1 | 1 | 1 | 2 | 6
Medium | 1 | 1 | 1 | 2 | 1
Low | 1 | 1 | 3 | 2 | 1
DM / mMtg / CLASS
BRD Miss / SRD Miss / Build Issue / Existing Issue / Performance Testing Issue
Code Defect
BRCC
Third Party
mMtg / Excalibur / OLB
SRD Miss
mMtg / CLASS / Excalibur / LCMS / Digital / EDH / SKP
SRD Miss / Code Defect / Build Issue / Third Party
mMtg
mMtg
Code Defect
SRD Miss / Code Defect / Existing Issue
SRD Miss
SRD Miss
DM / Target
LCMS
CAAP

## Slide 5: Sep Rel – Issue Count Overview - FY ‘24 vs FY ‘25 Releases
Business
Code error
Not coded to spec (code/config)
Soln reqmts
Gaps in detailed reqmts or tech soln
Training/Comm
Gaps in training, communication, PCM
Business reqmts
Gaps in detailed reqmts or tech soln
Third party
Gaps attributed to tech teams outside for CBPT
Deployment
Gaps in code packaging and deployment
Performance
Gaps in appln performance / slowness
Technology
Others
Chart: 
| Sep '25 | Jul '25 | Apr '25 | Feb '25 | Nov '24
Training/Comm/PCM | 3 | 1 | 2
Busn. Reqs | 5 | 5 | 2 | 4 | 1
Sol. Reqs | 7 | 3 | 8 | 2 | 2
Code | 19 | 14 | 13 | 20 | 6
Deployment | 2
Performance | 1
Third Party | 2 | 4 | 5 | 3
Chart: 
| Sep '24 | Jul '24 | Apr '24 | Feb '24 | Nov '23
Training/Comm/PCM | 1
Busn. Reqs | 1 | 1 | 1
Sol. Reqs | 5 | 4
Code | 2 | 1 | 4 | 8
Deployment | 1
Performance
Third Party | 3
13
PRJ
31
PRB.
5
ERRORS
FEB
17
PRJ
21
PRB.
2
ERRORS
APR
15
PRJ
31
PRB.
2
ERRORS
JUL
28
PRJ
13
PRB.
6
ERRORS
SEP
16
PRJ
17
PRB.
17
ERRORS
NOV
13
Chart: 
| FY24
Training/Comm/PCM | 1
Busn. Reqs | 3
Sol. Reqs | 9
Code | 15
Deployment | 1
Performance
Third Party | 3
89
PRJ
113
PRB.
34
ERRORS
FY 24
25
22
PRJ
38
PRB.
31
ERRORS
FEB
22
PRJ
25
PRB.
31
ERRORS
APR
23
PRJ
28
PRB.
27
ERRORS
JUL
37
PRJ
34
PRB.
36
ERRORS
SEP
44
PRJ
24
PRB.
9
ERRORS
NOV
8
22
24
17
Chart: 
| FY24
Training/Comm/PCM | 6
Busn. Reqs | 17
Sol. Reqs | 22
Code | 72
Deployment | 2
Performance | 1
Third Party | 14
148
PRJ
149
PRB.
134
ERRORS
FY 25
97
26

## Slide 6: Production Issues FY ‘24 vs FY ‘25 (based on issue open month)
Chart: 
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
FY '24 | 13 | 1 | 2 | 4 | 1 | 1 | 0 | 1 | 2 | 0 | 5 | 0
FY '25 | 6 | 1 | 1 | 23 | 0 | 18 | 7 | 1 | 15 | 18 | 27 | 3
Note:
Prod Issues are issues contributed by CBPT Technology. Existing prod issues / New requirements / Third Party Issues do not attribute to this count.
There are be a few issues for which the investigation is still in progress. They have been classified as Tech Issues temporarily. Once the analysis is complete, the counts may go down.

## Slide 7: Prod Issue Weight Calculation Matrix
S. No | Category of Impact | Impact | Answer
1 | Customer | Is there an impact to customer facing document? | Yes / No
 |  | Is the issue impacting a time sensitive activity? | Yes / No
 |  | Customer Escalation? | Yes / No
 |  | High value customer(s) impacted? | Yes / No
 |  | No. of Impacted accounts? | <Count>
2 | Financial and reporting | Is there any financial implication? | Yes / No
 |  | Risk reporting Impact? | Yes / No
 |  | Is there a GL impact? | Yes / No
 |  | Impacted $ amount? | <Amount>
3 | Regulatory | Is regulatory document not generated/sent? | Yes / No
 |  | Is regulatory report not generated? | Yes / No
 |  | Is there a non-conformance to risk appetite? | Yes / No
4 | Privacy | Is this a Privacy issue ? | Yes / No
5 | Technology & Business operations | Likely to delay a downstream system (feed dependency) coming up on time for business usage? | Yes / No
 |  | Does the issue prevent a batch process from starting or continuing in case already started? | Yes / No
 |  | Can the issue trigger or cause a potential system/application outage? | Yes / No
 |  | Is there an impact to the business operations process? | Yes / No
 |  | No. of Business Users Impacted? | <Count>
 |  | Is there a workaround? | Yes / No
Issue Weight | Criteria
10 | If any impact category is Yes and the number of accounts impacted is >= 100. OR If any impact category is Yes and the $ impact is >= 50K.
4 | If any impact category is Yes and the number of accounts impacted is >= 20 but < 100. OR If any impact category is Yes and the $ impact is >= 15K but < 50K. OR If the impacted customer is a High value customer.
3 | If any impact category is Yes and the number of accounts impacted is >1. OR If any impact category is Yes and the $ impact is < 15k. OR If any impact category is Yes and it is time sensitive. OR There is an impact to the Business Operations process and number of business users impacted is > 2.
2 | If any impact category is Yes, irrespective of whether a workaround is available. OR If at least 1 customer is impacted and a workaround is not available. OR If there is a Risk reporting impact and a workaround is not available.
1 | A workaround available and none of the other impact categories are yes.

## Slide 8: Prod Issue Weight Calculation Matrix – July Release
S. No | Category of Impact | Impact | Answer
1 | Customer | Is there an impact to customer facing document? | No
 |  | Is the issue impacting a time sensitive activity? | No
 |  | Customer Escalation? | No
 |  | High value customer(s) impacted? | No
 |  | No. of Impacted accounts? | N/A
2 | Financial and reporting | Is there any financial implication? | No
 |  | Risk reporting Impact? | No
 |  | Is there a GL impact? | No
 |  | Impacted $ amount? | N/A
3 | Regulatory | Is regulatory document not generated/sent? | No
 |  | Is regulatory report not generated? | No
 |  | Is there a non-conformance to risk appetite? | No
4 | Privacy | Is this a Privacy issue ? | No
5 | Technology & Business operations | Likely to delay a downstream system (feed dependency) coming up on time for business usage? | N/A
 |  | Does the issue prevent a batch process from starting or continuing in case already started? | No
 |  | Can the issue trigger or cause a potential system/application outage? | No
 |  | Is there an impact to the business operations process? | No
 |  | No. of Business Users Impacted? | >2
 |  | Is there a workaround? | Yes
Defect Weight | 1

## Slide 9
CB&PT Out of Release - 6 Months View
Intake # | Initiative Name | Implementation | PM | Change Type | Apps (Changed)
PRB0032950 | PRB0032950 | 10/10/2025 | Majinder | Problem Record | PCA/SAV
16298 | Migrate historical document from FileNet to ECM | 10/11/2025 | Sumit | Project | ECM
3060 | Project Light Year - CR120 | 10/11/2025 | Ananth | Project | ENVOY
16298 | Migrate historical document from FileNet to ECM | 10/18/2025 | Sumit | Project | Target
22502 | CRDS Archive on-boarding to ECM Shared Services | 10/18/2025 | Monika | MOPs | ECM
3745 | JEDI - Apollo Letters Decomm | 10/18/2025 | Sidhartha |  | RPE, DDGS
24683 | CAMLR Testing in Pilot 2 - DigiCore CR | 10/18/2025 | Sudarshi |  | DDGS
24628 | mMortgage Approval Letter | 10/18/2025 | Sudarshi |  | DDGS
23884 | Project Atticus | 10/18/2025 | Vini Virendra | Project | DDGS
16417 | CAAP SCM | 10/19/2025 | Sumit | SCM | CAAP
22632 | New Debit Card Issuance Request Signature Capture | 10/19/2025 | Monika | Project | DDGS, Channel Integrator , ECM, EDTS, CSP, RPE
22623 | Eliminate IMDS (Infoprint) dependency for DDGS letters | 10/19/2025 | Paramita | MOPs | DDGS
22958 | PBBT-22958 Update Form 13057 | 10/19/2025 | Naveen |  | DDGS
2800 | IDP - CR70 Tactical | 10/19/2025 | Aleksandra | CCR | mMortgage
23384 | Project Atticus | 10/19/2025 |  | MOPs | DDGS
24122 | F25-FLP-10573 Employee Purpose Loan Payment Amount and Term Mismatch | 10/19/2025 | Paramita | MOPs | DDGS
PRB0032917 | Renewal Document generated with incorrect Prime rate | 10/19/2025 | Subaleka | Problem Record | Excalibur
13117 | Low Cost Mandate | 11/4/2025 | Princy | Project | PCA/SAV
3745 | Project JEDI | 11/4/2025 | Sidhartha | Project | PCA/SAV
PRB0032876 | DDGS Autosys holiday calendar update for year 2026 and 2027 | 11/23/2025 | Subaleka | Problem Record | DDGS
PRB0032463 | JDBC driver version update to improve database performance | 12/6/2025 | Subaleka | Problem Record | DDGS
INTK-13868 & 23088 Ph1 | SDB-Annual Discounts & Abandonment Process | 12/6/2025 | Rohit |  | SDB
24263 | PBBT-24263 HPP Intro Rate offer - Wave 25 - Phase 2 LFA | 12/7/2025 | Deepali | MOPs | 
4196 | mMTG SCM | 1/17/2026 | Sumit | SCM | mMortgage
3249 | EDH to EDGE Phase 2D - QCPA | 2/14/2026 | FALGUNI |  | RPE, PCA/SAV
PBPTINTK-3924 | EDH to EDGE Stream 2E | 3/2/2026 | FALGUNI |  | 
13583 | CRI | 3/27/2026 | Sudarshi | Project | PCA/SAV

## Slide 10
CB&PT Environment View
G | Environment view
Comments: | ''PA' Nov major release environment 'P1' Oct release IDP + RESL projects testing env 'HF' env: Oct DDGS and Feb release testing env 'T4' env: Nov release UAT testing env
N | Not Started | G | In Progress/ On Track | Y | May Miss Target Date | R | Will Miss Target End | C | Complete

## Slide 11
Additional Agenda – April Release SIT Deliveries
Sr # | Recommendations | Plan | Pros | Cons
1 | Code delivery on 22nd Nov, provided there is no showstopper and interface/env is working fine. As of now, interface is not working in DIT for April release. Our functional testing status is good. | 1. DEV to perform DIT up to 22nd Nov and deploy code in SIT on 22nd Nov, end of day. 2. Sev 1's that introduce complete outage for all QA teams will be fixed between 22nd Nov and 6th Dec. 3. All Sev 1’s (with limited outage), Sev 2's and lower Sev’s will be triaged after 6th Dec. 4. Time permitting, AD will participate in Internal Variance meetings. 5. On 25th Nov, as Ph2 code will be merged with Ph1, any defect for Ph1 will not be promoted until Ph2 code moves on 6th Dec | 1. QA will be able to start testing as planned. 2. QA can test DDGS Flows first, while AD works on the end-to-end interface testing. 3. QA can test DM BRUL through stubs. This way functional testing can be performed 4. AD team will have opportunity to focus on DIT until 6th Dec. | 1. Sev 1's may impact MIA testing, as applicable. 2. QA will not have fully DIT tested code to start test.
2 | Shift the code delivery to 4th Dec (instead of 22nd Nov and 6th Dec) except funding functionality (Advancing section, EFT File, IBB Funding and Liability payout task). This piece will be delivered on 13th Dec. The delay is due to ongoing SRD feedback, updates, and discussions. | 1. AD to merge all changes planed for 22nd Nov and 6th Dec and continue DIT on the merged code till 6th Dec. 2. Instead of delivering code on 6th Dec, AD will work extra hours to pull up the delivery to 4th Dec. | 1. Simplified code versions in DIT and SIT ensuring focus on code quality and execution. 2. With no defect conversations, focus will be on delivery on 4th Dec. | 1. QA Testing cycle for MVP8.2 and Hopper 1 will be delayed by 8 days.
Problem Statement:
For the April Release, DIT was supposed to end on 22nd Nov. However, due to the reasons below there is a delay.
Overall release DIT is currently at 45% completion.
Reason for Delay:
DIT timelines were squeezed from 3 weeks to 2 weeks as the Feb release testing was using the same Dev env.
There was an ask to deploy code early in SIT for Hopper 2. As all code was required together, AD needed additional time.
The code merge of the projects in April release is complex and time consuming as the changes are to the same flows/interfaces.

## Slide 12
Release Status
Summary:
Warranty is complete. Summary of production issues are listed below:
  Production Issues: 41 [07 Scheduled, 34 Closed]
  Total Observations: 41
    Tech Issues (CBPT) : 29
      Code Defect: 19
      Solution Requirement Gap: 07
      Deferred Defect: 03
    Other Issues: 11
      Non CBPT/Third Party Issue: 02
      Business Requirement/Process Gap: 08
      Non-Issue: 01
    Rootcause Analysis in progress: 01
  Plan for Resolution/Closure: 41
    Upcoming fixes: 07
      18-Oct: 02
      19-Oct: 01
      16-Nov: 04
    Fixed: 27
    No fix required: 03
    Deferred with new CR/intake/Inc: 04
Open Risks / Issues: None
Awareness: Lower Env Sync up are planned.
Activity | Status | Start | End | Comments
BA |  |  |  | 
BRD / SRDs / CRs | C |  |  | 
AD |  |  |  | 
Infra Dependencies | C | - | - | 
MIP | C | Aug 22 | Sep 18 | 
B/O Matrix | C | Aug 18 | Sep 12 | 
SCM Updates | C | Aug 18 | Sep 12 | 
ACPs | C | Aug 18 | Sep 12 | 
OSI / Run Books | C | Aug 18 | Sep 12 | 
ADM Readiness | C | Aug 18 | Sep 12 | 
Deliverable Status
Release Lead: | Divyanshu Gupta | Release AD Lead: | Sivin Victor
TO / DXC PM: | Devika Gandhi / Chad Irvine | Release QA Lead: | Deborah Zhang
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete
W | Core Banking – (Sep 21, 2025) |  |  |  |  |  |  |  |  |  | 
Phase: | REQ | DES | CON | DIT | SIT | UAT | PAT | Scope: | 71 | 37 | Projects & MOPs
 | C | C | C | C | G | G | N |  |  | 34 | PRBs/INCs/Others
 | C | C | C | C | C | C | C |  |  |  | 
Apps: | 42 | 30 | CBPT |  | AIF, CAAP, CIBC R.Term, CLASS, COLT, DDGS, DDGS API, DM, DM (PEGA), ECM, EDTS, ENVOY, Excalibur, Excalibur API, Forms Management, IDP API, LCMS, LCMS API, Lending API, PCA/SAV, RPE, Remote Banking Batch, STB, TABS, W360 - FX, W360 - Non-Reg, W360 - RIF, W360 - RSP, W360 - TFSA, mMortgage |  |  |  |  |  | 
 |  | 12 | Non-CBPT |  | CASA, CIW, COINS (Host Facilities), COMPASS-AIM, ECIF, EDH, EDSF, GOW, Lending BI, MI Lending, PostEdge, eBanking |  |  |  |  |  | 
Release Triage #: | TR2025-PRG-038233 | SIT/UAT Env: | P1/T4
TO CIS / SRR #: | TO2024002460/SR054019 | Master Change #: | CHG1477270
QA |  |  |  | 
SIT | C | May 12 | Sep 05 | 
UAT | C | Jun 09 | Sep 18 | 
PAT | C | Aug 19 | Sep 17 | 
CAAP PTE | C | Aug 25 | Sep 12 | 
PIV Planning | G | Aug 25 | Sep 19 | 
CBPT Reg. | C | Aug 11 | Sep 17 | 
COMPASS Reg. | C | Aug 25 | Sep 17 | 
FNF Reg. | C | Aug 18 | Aug 29 | 
B/O Testing | C | Sep 15 | Sep 19 | 
PMO |  |  |  | 
Triages | C | Jul 14 | Sep 19 | 
CIRA | C | Jul 14 | Sep 19 | 
Gating | C | Jul 14 | Sep 19 | 

## Slide 13
Release Status
Summary:
Release is Red.
The impacted initiative listed below has testing delays caused by unresolved defects, SIT delays, and solution gaps, with key issues in data accuracy and formatting. UAT is dependent on E2E SIT which is delayed due to dependency on open defects from other teams (EDTS, GOW, Lending BI) Teams are prioritizing defect resolution and may re-baseline testing timelines if required.
Open Risks / Issues:
None
Awareness:
Lower Env Sync up are planned.
Activity | Status | Start | End | Comments
BA |  |  |  | 
BRD / SRDs / CRs | G |  |  | 
AD |  |  |  | 
Infra Dependencies | G | - | - | 
MIP | N | Oct 17 | Nov 14 | 
B/O Matrix | G | Oct 07 | Nov 14 | 
SCM Updates | N | Oct 13 | Nov 14 | 
ACPs | N | Oct 13 | Nov 14 | 
OSI / Run Books | N | Oct 13 | Nov 14 | 
ADM Readiness | N | Oct 13 | Nov 14 | 
Deliverable Status
Release Lead: | Anisah Patel | Release AD Lead: | Sivin Victor
TO / DXC PM: | Devika Gandhi / Chad Irvine | Release QA Lead: | Deborah Zhang
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete
R | Core Banking – (Nov 16, 2025) |  |  |  |  |  |  |  |  |  | 
Phase: | REQ | DES | CON | DIT | SIT | UAT | PAT | Scope: | 61 | 32 | Projects & MOPs
 | C | C | C | C | G | G | N |  |  | 29 | PRBs/INCs/Others
 | G | G | G | G | Y | R | N |  |  |  | 
Apps: | 32 | 26 | CBPT |  | AMS, CAAP, CI, CLASS, COLT, DDGS, DDGS API, DM, DM (PEGA), ECM, EDTS, ENVOY, Excalibur, FX, FirstLine.com, Forms Management, IMDS, LAS, LCMS, Lending API, PCA/SAV, RPE, STB, TABS, Target, mMortgage |  |  |  |  |  | 
 |  | 06 | Non-CBPT |  | COMPASS-AIM, Client Messaging Alert Broker (CMAB), ECIF, EDH, SKP (Vendor), eBanking |  |  |  |  |  | 
Release Triage #: | TR2025-PRG-038874 | SIT/UAT Env: | PA/T4
TO CIS / SRR #: | TO2024002460/SR054019 | Master Change #: | CHG1505987
QA |  |  |  | 
SIT | Y | Aug 04 | Oct 17 | 
UAT | R | Sep 22 | Nov 07 | 
PAT | N | Oct 13 | Nov 07 | 
CAAP PTE | N | N/A | N/A | No projects are making changes to CAAP
PIV Planning | N | Oct 13 | Nov 14 | 
CBPT Reg. | N | Oct 06 | Nov 10 | 
COMPASS Reg. | N | Oct 27 | Nov 07 | 
FNF Reg. | N | Oct 13 | Oct 31 | 
B/O Testing | N | Nov 10 | Nov 14 | 
PMO |  |  |  | 
Triages | G | Sep 16 | Nov 14 | 
CIRA | G | Sep 16 | Nov 14 | 
Gating | G | Sep 16 | Nov 14 | 
Status | Phase | Item
R | UAT | 3517¦Property Insurance Cancellation: Red due to unresolved defects, SIT delays, and eight solution gaps missed during internal testing. Key issues include data mismatches, incorrect date formats, and pending updates, with revised SIT end dates set for dependent Lending BI to Oct 13. The go-to-green plan focuses on completing one full end-to-end data flow and QA risk assessment.
Y | SIT | 3517¦Property Insurance Cancellation: Yellow as extraction issues have been addressed but need better accuracy; updated fixes to be addressed by AD and will be deployed by Oct 09. Testing to be performed after deployment. 4149¦NSOD Forms Update: Yellow as Envoy UI issue has been resolved and SIT code to be deployed Oct 10, and end-to-end retesting on Oct 13.

## Slide 14: November 16th Release Scope
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete
Item | PM | PD | Type | REQ | DEV | QA | Apps | Coins Dependent
16355 ¦ Bill 72 COPS Monthly Flat Fee (Nov - CRs) | Princy | Panagiotoglou, Fred | PRJ | - | - | G | DDGS, RPE, ECM, Client Messaging Alert Broker (CMAB) | 
16393 ¦ Credit Maintenance Platform - Nov Release | Kanyinsola | Dykeman, Christina M | PRJ | - | - | G | DM | 
23572 ¦ RESL POD Shift Left - Nov Release | Prateek | Sudan, Arpan | PRJ | - | - | G | mMortgage, LCMS | 
23978 ¦ Include Simplii Accounts in DM Global Unsecured Debt Calculation | Kanyinsola | Dykeman, Christina M | PRJ | - | - | G | DM | 
2616 ¦ Renewal Due Diligence MVP 2.2 | Rachel | Sudan, Arpan | PRJ | - | - | G | mMortgage, Excalibur, DDGS, Lending API | 
3069 ¦ Guardian | Joy Rosalynn | Dykeman, Christina M | PRJ | - | - | G | mMortgage, Lending API, EDTS, EDH, SKP (Vendor) | 
3291 ¦ Client Level Pricing | Naveed | Sudan, Arpan | PRJ | - | - | G | mMortgage, Excalibur | 
3517 ¦ Property Insurance Cancellation | Reshma | Dykeman, Christina M | PRJ | - | - | R | DDGS, TABS, ECM, EDTS | 
3745 ¦ Project JEDI | Sidhartha | Panagiotoglou, Fred | PRJ | - | - | G | STB, COLT, CI, FX | Yes
3796 ¦ CLD and Repricing Letters - Imaging in ECM | Nikita | Dykeman, Christina M | PRJ | - | - | G | CLASS, DDGS, IMDS, RPE | 
4313 ¦ Digital Use Cases: Reverse Franchising | Kanyinsola | Dykeman, Christina M | PRJ | - | - | G | Lending API, eBanking, ECIF | 
4356 ¦ Credit Bureau Online Services Enhancements - Add Telco Trades & IDX Score | Ananth | Dykeman, Christina M | PRJ | - | - | G | DM, LCMS, CAAP, COMPASS-AIM | 
13812 ¦ mMortgage Property Details Updates | Ganesh | Sahni, Rachna | MOP | - | - | G | mMortgage | 
13832/4409 ¦ DM Relationships 4,5,6,7 to be Excluded from Auto-Approval | Onkar | Sahni, Rachna | MOP | - | - | G | DM (PEGA) | 
13920 ¦ Deferred Interest Renewal Package Generation - CMC Mortgages | Ganesh | Sahni, Rachna | MOP | - | - | G | Excalibur | 
16718 ¦ RAF Program Expansion | Adinarayana Murthy | Sahni, Rachna | MOP | - | - | G | RPE | 
17774 ¦ AMS 2025 | Neha Vineet | Sahni, Rachna | MOP | - | - | G | Excalibur, DDGS, IMDS | 
22379 ¦ Risk Issue 7308 - RESL 2.0. Values to Populate CLASS 2012 to Current Data | Neha Vineet | Sahni, Rachna | MOP | - | - | G | CLASS | 
22425 ¦ MVP16 CR65 Excalibur LFA to Appraised Value | Neha Vineet | Sahni, Rachna | MOP | - | - | G | Excalibur | 
22623 ¦ Eliminate IMDS (Infoprint) dependency for DDGS letters | Paramita | Sahni, Rachna | MOP | - | - | N | DDGS | 
23113 ¦ Unclaimed Balances Records transfer from NAS to ECM | Adinarayana Murthy | Sahni, Rachna | MOP | - | - |  | ECM | 
23266 ¦ Ingestion Error Fix - MVP 1 | Ganesh | Sahni, Rachna | MOP | - | - | G | LCMS | 
23365 ¦ LCMS Funding Condition Issues | Neha Vineet | Sahni, Rachna | MOP | - | - | G | LCMS | 
23515 ¦ Update Creditor Insurance Product Summarys for Fax Number | Adinarayana Murthy | Sahni, Rachna | MOP | - | - | N | DDGS, DDGS API, Forms Management | 
23538 ¦ LAS Feed - AML-TMS (Map-585) - Decommission (TO2025000894 - SR054809) | Rajib | Sahni, Rachna | MOP | - | - | OO | LAS | 
23552 ¦ Excalibur to RCDW Month End Interest Calculation Update | Neha Vineet | Sahni, Rachna | MOP | - | - | G | Excalibur | 
23725 ¦ AML CDCC Sustainment Project | Neha Vineet | Sahni, Rachna | MOP | - | - | N | EDTS | 
4105 ¦ Client at Risk | Neha Vineet | Sahni, Rachna | MOP | - | - | G | Excalibur | 
22622 ¦ Form Modernization Stream3 | Dheeraj |  | PRJ | - | - |  | IMDS, DDGS | 
Notes: 3-Apr
PRB0029495 | Document Status on the DDGS LAS UI for the document ‘LAS Personal Loan Annual Confirmation Letter ‘ does not accurately reflect the printing status once the document is printed.
Suniti
PRB
-
-
DDGS

## Slide 15: November 16th Release Scope
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete
Item | PM | PD | Type | REQ | DEV | QA | Apps | Coins Dependent
4149 ¦ NSOD Forms Update | Onkar | Sahni, Rachna | MOP | - | - | Y | RPE, DDGS, ECM, IMDS, ENVOY, PCA/SAV | 
PRB0032177 ¦ E37 External Table Upload issue | Subaleka | Gupta, Suniti | PRB | - | - | N | DM | 
PRB0032456 ¦ unassigned files with User ID-Shortage workgroup on LCMS LP | Subaleka | Gupta, Suniti | PRB | - | - | N | LCMS | 
PRB0032484 ¦ Issue with BRUL20703 - Deferred Income Indicator | Subaleka | Gupta, Suniti | PRB | - | - | N | DM | 
PRB0032489 ¦ Real Time Data issue at LCMS end for create date field | Subaleka | Gupta, Suniti | PRB | - | - | N | Lending API | 
PRB0032598 ¦ Excalibur – Remaining amortization issue on renewal confirmation letter for VRM mortgages | Subaleka | Gupta, Suniti | PRB | - | - | N | Excalibur | 
PRB0032654 ¦ Defect 4171 - Deal originated from mMTG with Variable product having any promotional offers we could see Approval/Condit... | Subaleka | Gupta, Suniti | PRB | - | - | N | LCMS | 
PRB0032685 ¦ Issue with BRUL20853 Do not Decline Refer | Subaleka | Gupta, Suniti | PRB | - | - | N | DM | 
PRB0032734 ¦ Excalibur – Incorrect Prepayment calculation for multiple prepayment reversal >= 50K with same posting date & transactio... | Subaleka | Gupta, Suniti | PRB | - | - | N | Excalibur | 
PRB0032786 ¦ GVS FAIL recd from DM not reflecting on MMTG, system retained GVS PASS incorrectly. | Subaleka | Gupta, Suniti | PRB | - | - | N | LCMS | 
PRB0032788 ¦ Fix shell script to prevent external upload job failure | Subaleka | Gupta, Suniti | PRB | - | - | N | DM | 
PRB0032791 ¦ Pentest Fixes 2025 | Subaleka | Gupta, Suniti | PRB | - | - | N | FirstLine.com | 
PRB0032826 ¦ LCMS Glossary French Description | Subaleka | Gupta, Suniti | PRB | - | - | N | LCMS | 
PRB0032836 ¦ COINS STB ATDF Fix | Shannon | Kohli, Rajesh | PRB | - | - | G | STB | 
PRB0032846 ¦ Log file increase for the MMTG CP API | Subaleka | Gupta, Suniti | PRB | - | - | N | Lending API | 
PRB0032849 ¦ To fix GL mapping for FLM PREPY transactions | Subaleka | Gupta, Suniti | PRB | - | - | N | Target | 
PRB0032862 ¦ Fortify Security Scan Issues | Subaleka | Gupta, Suniti | PRB | - | - | N | LCMS | 
PRB0032867 ¦ TBD Funding method | Subaleka | Gupta, Suniti | PRB | - | - | N | LCMS | 
PRB0032891 ¦ Create new job for Simplii ECM drop1 | Subaleka | Gupta, Suniti | PRB | - | - | N | Target | 
PRB0032894 ¦ HPP Mtge Attachment Issue Fix | Subaleka | Gupta, Suniti | PRB | - | - | N | CLASS | 
PRB0032895 ¦ Subject Property issue fix LFA | Subaleka | Gupta, Suniti | PRB | - | - | N | CLASS | 
PRB0032939 ¦ Cancellation At the time of invocation target exception | Subaleka | Gupta, Suniti | PRB | - | - | N | LCMS | 
PRB0032955 ¦ PRB0032955 Resync Nov 2025 release | Subaleka | Gupta, Suniti | PRB | - | - |  | CLASS | 
PRB0057001 ¦ Intermittent Slowness due to Purge Job in Servicing Portal | Kavita | Dominic, Roshini | PRB | - | - | N | mMortgage | 
3504 ¦ Risk AMS Triad/TAD infra Upgrade | Sumit | Sahni, Rachna | CCR | - | - | G | AMS, CLASS | 
2800 ¦ IDP MVP3 - CRs and Defect fixes | Aleksandra | Panagiotoglou, Fred | MNT | - | - | G | mMortgage, LCMS | 
PCABASE54 ¦ PCABASE54 | Majinder | Power, Christopher | MNT | - | - | OO | PCA/SAV | 
24025 ¦ Non Business Days Update for year 2026 | Subaleka | Gupta, Suniti | OR | - | - | OO | Excalibur | 
22345 ¦ Mortgage Discharge Collatoral Update | Naveen | Sahni, Rachna |  | - | - | OO | ENVOY, DDGS | 
22958 ¦ PBBT-22958 Update Form 13057 | Naveen | Sahni, Rachna |  | - | - |  | DDGS | 
24287 ¦ PBBt-24287 Update Form 3958 BIL (Wires T&C) | Ganesh | Sahni, Rachna | MOP | - | - |  | DDGS | 
PBBT-16444 ¦ IPS Data Request | Onkar | Sahni, Rachna | MOP | - | - |  | IPS | 
Notes: 3-Apr
PRB0029495 | Document Status on the DDGS LAS UI for the document ‘LAS Personal Loan Annual Confirmation Letter ‘ does not accurately reflect the printing status once the document is printed.
Suniti
PRB
-
-
DDGS

## Slide 16
November 16th Release Project SIT, UAT, & PAT Timelines
 | Name | Impl Date | Phase | START | END | 7-Jul | 11-Jul | 14-Jul | 18-Jul | 21-Jul | 25-Jul | 28-Jul | 1-Aug | 4-Aug | 8-Aug | 11-Aug | 15-Aug | 18-Aug | 22-Aug | 25-Aug | 29-Aug | 1-Sep | 5-Sep | 8-Sep | 12-Sep | 15-Sep | 19-Sep | 22-Sep | 26-Sep | 29-Sep | 3-Oct | 6-Oct | 10-Oct | 13-Oct | 17-Oct | 20-Oct | 24-Oct | 27-Oct | 31-Oct | 3-Nov | 7-Nov | 10-Nov | 14-Nov | 16-Nov
3745 | Project JEDI | 16-Nov | SIT | 15-Sep-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 15-Sep-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2616 | Renewal Due Diligence | 16-Nov | SIT | 3-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 13-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3291 | Client Level Pricing | 16-Nov | SIT | 6-Aug-25 | 26-Sep-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 29-Sep-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3517 | Property Insurance Cancellation | 16-Nov | SIT | 7-Aug-25 | 19-Sep-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 22-Sep-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3503 | CIPS Tranche-3 Ph2 | 16-Nov | SIT | 13-Oct-25 | 17-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3796 | CLD and Repricing Letters - Imaging in ECM | 16-Nov | SIT | 3-Sep-25 | 3-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 6-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4356 | Credit Bureau Online Services Enhancements - Add Telco Trades & IDX Score | 16-Nov | SIT | 22-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 13-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3069 | Guardian | 16-Nov | SIT | 4-Aug-25 | 26-Sep-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 29-Sep-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4313 | Digital Use Cases: Reverse Franchising | 16-Nov | SIT | 15-Sep-25 | 17-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 20-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4149 | NSOD Forms Update | 16-Nov | SIT | 11-Aug-25 | 29-Aug-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 22-Sep-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
17774 | AMS 2025 | 16-Nov | SIT | 15-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 13-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
22379 | Risk Issue 7308 - RESL 2.0. Values to Populate CLASS 2012 to Current Data | 16-Nov | SIT | 29-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 13-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
22425 | MVP16 CR65 Excalibur LFA to Appraised Value | 16-Nov | SIT | 29-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 13-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
23266 | Ingestion Error Fix - MVP 1 | 16-Nov | SIT | 15-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 13-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
22623 | Eliminate IMDS (Infoprint) dependency for DDGS letters | 16-Nov | SIT | 13-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4105 | Client at Risk | 16-Nov | SIT | 22-Sep-25 | 3-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 6-Oct-25 | 17-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
23365 | LCMS Funding Condition Issues | 16-Nov | SIT | 15-Sep-25 | 3-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 6-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
23552 | Excalibur to RCDW Month End Interest Calculation Update | 16-Nov | SIT | 29-Sep-25 | 17-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 20-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
23725 | AML CDCC Sustainment Project | 16-Nov | SIT | 6-Oct-25 | 17-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 20-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3504 | Risk AMS Triad/TAD infra Upgrade | 16-Nov | SIT | 14-Jul-25 | 8-Aug-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 11-Aug-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 17
November 16th Release Project SIT, UAT, & PAT Timelines
 | Name | Impl Date | Phase | START | END | 7-Jul | 11-Jul | 14-Jul | 18-Jul | 21-Jul | 25-Jul | 28-Jul | 1-Aug | 4-Aug | 8-Aug | 11-Aug | 15-Aug | 18-Aug | 22-Aug | 25-Aug | 29-Aug | 1-Sep | 5-Sep | 8-Sep | 12-Sep | 15-Sep | 19-Sep | 22-Sep | 26-Sep | 29-Sep | 3-Oct | 6-Oct | 10-Oct | 13-Oct | 17-Oct | 20-Oct | 24-Oct | 27-Oct | 31-Oct | 3-Nov | 7-Nov | 10-Nov | 14-Nov | 16-Nov
PRB0032177 | E37 External Table Upload issue | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032598 | Excalibur – Remaining amortization issue on renewal confirmation letter for VRM mortgages | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032484 | Issue with BRUL20703 - Deferred Income Indicator | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0057001 | Intermittent Slowness due to Purge Job in Servicing Portal | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032734 | Excalibur – Incorrect Prepayment calculation for multiple prepayment reversal >= 50K with same posting date & transaction | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032456 | Unassigned files with User ID-Shortage workgroup on LCMS LP | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032685 | Issue with BRUL20853 Do not Decline Refer | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032489 | Real Time Data issue at LCMS end for create date field | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032788 | Fix shell script to prevent external upload job failure | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032791 | Pentest Fixes 2025 | 16-Nov | SIT | 6-Oct-25 | 17-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 20-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032654 | Defect 4171 - Deal originated from mMTG with Variable product having any promotional offers we could see Approval/Condit... | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032826 | LCMS Glossary French Description | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032786 | GVS FAIL recd from DM not reflecting on MMTG, system retained GVS PASS incorrectly. | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032846 | Log file increase for the MMTG CP API | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032849 | To fix GL mapping for FLM PREPY transactions | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PCABASE54 | PCABASE54 | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032867 | TBD Funding method | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032862 | Fortify Security Scan Issues | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 18
November 16th Release Project SIT, UAT, & PAT Timelines
 | Name | Impl Date | Phase | START | END | 7-Jul | 11-Jul | 14-Jul | 18-Jul | 21-Jul | 25-Jul | 28-Jul | 1-Aug | 4-Aug | 8-Aug | 11-Aug | 15-Aug | 18-Aug | 22-Aug | 25-Aug | 29-Aug | 1-Sep | 5-Sep | 8-Sep | 12-Sep | 15-Sep | 19-Sep | 22-Sep | 26-Sep | 29-Sep | 3-Oct | 6-Oct | 10-Oct | 13-Oct | 17-Oct | 20-Oct | 24-Oct | 27-Oct | 31-Oct | 3-Nov | 7-Nov | 10-Nov | 14-Nov | 16-Nov
PRB0032894 | HPP Mtge Attachment Issue Fix | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032895 | Subject Property issue fix LFA | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032891 | Create new job for Simplii ECM drop1 | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
23978 | Include Simplii Accounts in DM Global Unsecured Debt Calculation | 16-Nov | SIT | 6-Oct-25 | 22-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 23-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
23572 | MOD POD - RESL POD Shift Left Nov Release | 16-Nov | SIT | 8-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 6-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13832/4409 | DM Relationships 4,5,6,7 to be Excluded from Auto-Approval | 16-Nov | SIT | 22-Sep-25 | 3-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 6-Oct-25 | 17-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PBBT-23538 | LAS Feed - AML-TMS (Map-585) - Decommission (TO2025000894 - SR054809) | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
16718 | RAF Program Expansion | 16-Nov | SIT | 15-Sep-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 15-Sep-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13920 | Deferred Interest Renewal Package Generation - CMC Mortgages | 16-Nov | SIT | 15-Sep-25 | 26-Sep-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 29-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13812 | mMortgage Property Details Updates | 16-Nov | SIT | 22-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 13-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
23113 | Unclaimed Balances Records transfer from NAS to ECM | 16-Nov | SIT | 22-Sep-25 | 10-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 6-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
23515 | Update Creditor Insurance Product Summarys for Fax Number | 16-Nov | SIT | 13-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 13-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
16355 | Bill 72 COPS Monthly Flat Fee (Nov - CRs) | 16-Nov | SIT | 22-Sep-25 | 17-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 20-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032836 | COINS STB ATDF Fix | 16-Nov | SIT | 2-Sep-25 | 26-Sep-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 7-Oct-25 | 22-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032939 | Cancellation At the time of invocation target exception | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
22958 | PBBT-22958 Update Form 13057 | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
22345 | Mortgage Discharge Collatoral Update | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
24025 | Non Business Days Update for year 2026 | 16-Nov | SIT | 20-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2800 | IDP MVP3 - CRs and Defect fixes | 16-Nov | SIT | 6-Oct-25 | 17-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 20-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
16393 | Credit Maintenance Platform - Nov Release | 16-Nov | SIT | 6-Oct-25 | 24-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 27-Oct-25 | 31-Oct-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 19
November 16th Release Project SIT, UAT, & PAT Timelines
 | Name | Impl Date | Phase | START | END | 7-Jul | 11-Jul | 14-Jul | 18-Jul | 21-Jul | 25-Jul | 28-Jul | 1-Aug | 4-Aug | 8-Aug | 11-Aug | 15-Aug | 18-Aug | 22-Aug | 25-Aug | 29-Aug | 1-Sep | 5-Sep | 8-Sep | 12-Sep | 15-Sep | 19-Sep | 22-Sep | 26-Sep | 29-Sep | 3-Oct | 6-Oct | 10-Oct | 13-Oct | 17-Oct | 20-Oct | 24-Oct | 27-Oct | 31-Oct | 3-Nov | 7-Nov | 10-Nov | 14-Nov | 16-Nov
CBPT Applications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Lending API |  | 16-Nov | PAT | 13-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DDGS |  | 16-Nov | PAT | 13-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DM & LCMS |  | 16-Nov | PAT | 13-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Envoy & RPE |  | 16-Nov | PAT | 13-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Excalibur |  | 16-Nov | PAT | 13-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TABS |  | 16-Nov | PAT | 13-Oct-25 | 7-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 20: November 16th Release Infrastructure Dependencies
# | Project | Short Description | Apps | Owner | TO CIS # | TO/DXC PM | Target Date | Comments/ Status
1 | 3504 ¦ Risk AMS Triad/TAD infra Upgrade | 1. Upgrade Linux servers to higher version (6.1 to 7.9) 2. Upgrade WebSphere and JBOSS to higher version 3. Upgrade windows server from 2012 to higher version 4. Upgrade SQL DB to higher version | CLASS, AMS | Sumit | TO2025000651 / SR054634 | Ireland, Kevin | Nov 09: (Backup: Nov 11/12 as applicable) Pre prod activity + Data Migration with AMS CHG record. Nov 16: AMS – DNS pointing from Old server to new server. CLASS – Batch changes with code promotion to change the length of a file. | In Progress

## Slide 21: November 16th Release PIV – Initiatives with PIV
Initiatives Performing PIV |  | 
Initiatives with PIV ON Implementation Day |  | 
Initiatives Performing HC ON Implementation Day |  | 
Initiatives with PIV AFTER Implementation Day |  | 
Intake # | Initiative Name | PM | Change Type | PIV Required | PIV Planning | PIV Test Case Status | PIV Planning ETA | PIV on Imp. Date | Business Health Check on Imp. day | PIV After Imp. Date

## Slide 22: November 16th Release PIV – Initiatives without PIV
Intake # | Initiative Name | PM | Change Type | PIV Required | PIV Planning | PIV Test Case Status | PIV Planning ETA | PIV on Imp. Date | Business Health Check on Imp. day | PIV After Imp. Date
Initiatives without PIV | 17 | 

## Slide 23: November 16th Release Readiness
N | Not Started | G | In Progress/ On Track | Y | May Miss Target Date | R | Will Miss Target End | C | Complete
SCOPE
Project/ MOPS | OR/ Campaigns / Maint. | Incidents/ PRB Records | CCR | Others | Total
31 | 3 | 23 | 1 | - | 58
Scope | Schedule | Funct. Testing | Env. | Rel. Readiness | Code Freeze | Overall Status
G | G | R | G | G | G | R
ACTIVITY | DETAILS | TARGET | ETA | %
Design Review | In Progress: AMS ¦ API Lending ¦ CAAP ¦ COLT ¦ DDGS ¦ EDTS ¦ ENVOY ¦ FirstLine.com ¦ LCMS ¦ mMortgage ¦ RPE ¦ TABS ¦ Target ¦ CLASS ¦ Excalibur ¦ LAS Completed: CI ¦ DM ¦ FX ¦ PCA/SAV ¦ STB | 21 Sep | 17 Oct | 27%
Code Review | In Progress: AMS ¦ API Lending ¦ CAAP ¦ CLASS ¦ COLT ¦ DDGS ¦ EDTS ¦ ENVOY ¦ Excalibur ¦ FirstLine.com ¦ LAS ¦ LCMS ¦ mMortgage ¦ RPE ¦ TABS ¦ Target ¦ DM Completed: CI ¦ FX ¦ PCA/SAV ¦ STB | 21 Sep | 17 Oct | 12%
Diff Report Review (SIT) | In Progress: AMS ¦ API Lending ¦ CAAP ¦ CLASS ¦ COLT ¦ DDGS ¦ DM ¦ EDTS ¦ ENVOY ¦ Excalibur ¦ FirstLine.com ¦ LAS ¦ LCMS ¦ mMortgage ¦ RPE ¦ TABS ¦ Target Completed: CI ¦ FX ¦ PCA/SAV ¦ STB | 21 Sep | 17 Oct | 7%
Infra Readiness Status | 3504 ¦ Risk AMS Triad/TAD infra Upgrade: Upgrade of Linux servers, WebSphere, JBOSS, Windows server and SQL DB to higher version. ETA: 9th Nov, 2025 | 9 Nov | 9 Nov | 0%
ADM External Review | In Progress: AMS ¦ API Lending ¦ CAAP ¦ CI ¦ CLASS ¦ COLT ¦ DDGS ¦ EDTS ¦ ENVOY ¦ FirstLine.com ¦ FX ¦ LAS ¦ LCMS ¦ mMortgage ¦ RPE ¦ STB ¦ TABS ¦ Target ¦ DM ¦ Excalibur Completed: PCA/SAV | 19 Oct | 19 Oct | 13%
ADM Operational Review | In Progress: AMS ¦ API Lending ¦ CAAP ¦ CLASS ¦ COLT ¦ DDGS ¦ DM ¦ EDTS ¦ ENVOY ¦ FirstLine.com ¦ LAS ¦ LCMS ¦ mMortgage ¦ RPE ¦ TABS ¦ Target ¦ Excalibur Completed: CI ¦ FX ¦ PCA/SAV ¦ STB | 19 Oct | 19 Oct | 13%
QA Regression and External Review | QA Regression Testing – 1828 / 8808 TC’s QA External Review – 0 / 58 projects | 7 Nov | 7 Nov | 10%
PIV Planning | PIV TC’s Execution in Test Env – Not Started PIV Users confirmation – Not Started ADM/QC support for PIV – Not Started | 7 Nov | 7 Nov | 0%
Impl Readiness | Backout Matrix review – In Progress Backout testing scenario walkthrough and Testing – Not Started MIP walkthrough and Sign Off – Not Started Change Records and Resource Alignment – Not Started SCM – In Progress ACP – In Progress OP Docs – In Progress | 7 Nov | 7 Nov | 11%
FOCUS
ISSUES
KEY INITIATIVES | APPS
16355 ¦ Bill 72 COPS Monthly Flat Fee (Nov - CRs) 23572 ¦ RESL POD Shift Left - Nov Release 2616 ¦ Renewal Due Diligence MVP 2.2 3069 ¦ Guardian 3291 ¦ Client Level Pricing 3517 ¦ Property Insurance Cancellation 3745 ¦ Project JEDI 3796 ¦ CLD and Repricing Letters - Imaging in ECM 4313 ¦ Digital Use Cases: Reverse Franchising 4356 ¦ Credit Bureau Online Services Enhancements - Add Telco Trades & IDX Score | CBPT: 26 Non CBPT: 6
Status | Phase | Item
R | UAT | 3517¦Property Insurance Cancellation: Unresolved defects, SIT delays, and eight solution gaps. Revised SIT end dates set for October 13.
Y | SIT | 3517¦Property Insurance Cancellation: Extraction issues have been addressed but need better accuracy. 4149¦NSOD Forms Update: Envoy UI issue has been resolved and SIT code to be deployed Oct 10, and end-to-end retesting on Oct 13.

## Slide 24: November 16th Release Project Backout Matrix

## Slide 25: November 16th Release Out of Release Scope
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete
Summary:
None
Open Risks / Issues:
None
Awareness:
None
C​ | T​ | Imp​ | Item​ | PM​ | Type​ | REQ​ | DEV​ | QA​ | Apps​
 |  |  | None |  |  |  |  |  | 
Notes: 3-Apr
PRB0029495 | Document Status on the DDGS LAS UI for the document ‘LAS Personal Loan Annual Confirmation Letter ‘ does not accurately reflect the printing status once the document is printed.
Suniti
PRB
-
-
DDGS

## Slide 26: November 16th Release Projects Backout Testing

## Slide 27
Application | Tech Lead
AMS | Samidi, Shashi
API Lending | Shinde, Bhagyashree ¦ Jayakumar, Apsara Malar ¦ Sharma, Vishruth
CAAP | Vhanmane, Vaibhav Uttam
CI | Foster, Shannon
CLASS | Singh, Madan ¦ Yadav, Kiran ¦ Kulkarni, Ninad Girish
COLT | Gonsalves, Mark ¦ Harding, Owen
DDGS | Zhang, Cher ¦ Kotni, Prasanna ¦ Desai, Vini Virendra
DM | Patel, Rushikesh Himanshubhai ¦ Band, Vaibhav Eknathrao ¦ Bodara, Asav ¦ Soni, Pushpendra
EDTS | Raza, Fyma
ENVOY | Mandi, Sreenath ¦ Rathore, Pavan ¦ Zhu, Jackson
Excalibur | Bugidi, Nagaraju ¦ Jahan, Amreen ¦ Agarwal, Niti
FirstLine.com | Shirode, Richa ¦ Verma, Priyanka
FX | Foster, Shannon
LAS | Yadav, Kiran ¦ Singh, Madan ¦ Kulkarni, Ninad Girish
LCMS | Nguyen, Anh Tuan ¦ Jain, Neeraj
mMortgage | Singh, Amit ¦ Chavan, Snehal Anil
PCA/SAV | Chamiraju, Sudheera Dattatreya 1 ¦ MacNeil, Natalie
RPE | Mandi, Sreenath ¦ Rathore, Pavan ¦ Sahoo, Deepak
STB | Foster, Shannon
TABS | Amrutkar, Mukul ¦ Kaushik, Rashmi ¦ Patanwar, Tarun
Target | Shirode, Richa ¦ Verma, Priyanka
November 16th Release ADM Leads (Draft)

## Slide 28
App / Group | PM/Lead | Available 5am-12pm | Changes planned | Contact Name & Phone Number
ECIF Services | Anisah |  |  | a. Mailbox.ECIFBaseEssential@cibc.com / Pager - 416 725 7107 (24*7 Support)​ b. harish1.kumar@cibc.com ¦ 647-270-2619 c. AdeshKumar.Bhati@CIBC.com / Adesh Kumar Bhati, (416-272-3493)
CGMI | Anisah |  |  | Ken Plowman Telephone 416-640-8927 ¦ Cell 416-315-9413 Toll Free 866-414-9109 x 8927 ken.plowman@canadaguaranty.ca
CMHC | Anisah |  |  | On Call: (613) 292-2880
GEMI | Anisah |  |  | Level 1:​​​ productionsupport@sagen.ca Level 2:​​​ Sabri.Madaoui@Sagen.ca ¦ 416-986-7156
TransUnion | Anisah |  |  | servicedesk@transunion.ca ¦ Support Desk: 905-570-1952
Equifax | Anisah |  |  | Support Desk: 1-800-387-9986
TEM | Tina Mallick |  |  | P1, T4, (+91 8697310205
Sep 21st Release App Availability

## Slide 29: Core Banking Release - Nov 16th – Outstanding Items
Intake # | Initiative Name | PM | Director | CIRA Status | UAT Status | Gated | Notes
Item | Application/Scope | Status | Notes
Backout testing |  |  | 
ACP |  |  | 
OSI |  |  | 
SCM |  |  | 
Item | Open Risks
Core Banking Release SCR Gate | UAT CIRA
EDTS Tungsten WMF Gate | UAT
Gates:
Projects:
Other Items:

## Slide 30
Release Status
Summary:
Release is Green
Open Risks / Issues:
None
Awareness:
Activity | Status | Start | End | Comments
BA |  |  |  | 
BRD / SRDs / CRs | G |  |  | 
AD |  |  |  | 
Infra Dependencies | N | - | - | 
MIP | N | Dec 29 | Jan 23 | 
B/O Matrix | N | Dec 29 | Jan 23 | 
SCM Updates | N | Dec 29 | Jan 23 | 
ACPs | N | Dec 29 | Jan 23 | 
OSI / Run Books | N | Dec 29 | Jan 23 | 
ADM Readiness | N | Dec 29 | Jan 23 | 
Deliverable Status
Release Lead: | Anisah Patel | Release AD Lead: | Sivin Victor
TO / DXC PM: | Devika Gandhi / Chad Irvine | Release QA Lead: | Deborah Zhang
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete
G | Core Banking – (Feb 1, 2026) |  |  |  |  |  |  |  |  |  | 
Phase: | REQ | DES | CON | DIT | SIT | UAT | PAT | Scope: | 20 | 13 | Projects & MOPs
 | C | C | C | C | G | G | N |  |  | 7 | PRBs/INCs/Others
 | G | G | G | G | G | N | N |  |  |  | 
Apps: | 25 | 16 | CBPT |  | CAAP, CIBC R.Term, CLASS, DDGS, DM, ECM, Excalibur, Forms Management, KC, LCMS, Lending API, mMortgage, PostEdge, RPE, TABS, Target |  |  |  |  |  | 
 |  | 9 | Non-CBPT |  | Auth Hub, CCARS, CIW, eBanking, ECIF, EDSF, EPC, Fraud Analyst Engine (OLB), Lending BI |  |  |  |  |  | 
Release Triage #: |  | SIT/UAT Env: | 
TO CIS / SRR #: |  | Master Change #: | 
QA |  |  |  | 
SIT | G | Oct 20 | Nov 28 | 
UAT | N | Dec 1 | Dec 26 | 
PAT | N | Dec 29 | Jan 16 | 
CAAP PTE | N | Jan 5 | Jan 16 | 
PIV Planning | N | Jan 12 | Jan 23 | 
CBPT Reg. | N | Jan 12 | Jan 23 | 
COMPASS Reg. | N | Jan 12 | Jan 23 | 
FNF Reg. | N | Jan 5 | Jan 16 | 
B/O Testing | N | Jan 12 | Jan 23 | 
PMO |  |  |  | 
Triages | N | Oct 14 | Jan 16 | 
CIRA | N | Oct 14 | Jan 16 | 
Gating | N | Oct 14 | Jan 23 | 
Status | Phase | Item
Y | SIT | 4114 ¦ Digital Switch Pre-Qualification: The team is missing several approvals for design for CR5. The team is still solutioning CR29, causing a delay.

## Slide 31: February 1st Release Scope
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete
Item | PM | PD | Type | REQ | DEV | QA | Apps | Coins Dependent
16732 ¦ AVM Strategy - CMHC to decomission CVI message | Faisal | Sudan, Arpan | PRJ | - | - |  | DM, LCMS, mMortgage, CLASS, EDH, Lending BI | 
2616 ¦ Renewal Due Diligence MVP3 | Adrina | Sudan, Arpan | PRJ | - | - |  | mMortgage, DDGS, Excalibur | 
2754 ¦ RAMP2 January 2026 Release | Ifeanyi | Panagiotoglou, Fred | PRJ | - | - | N | CIBC R.Term, DDGS, Forms Management, KC | 
2800 ¦ IDP - MVP3 CR49 Split & Merge, CR50, CR70 | Aleksandra | Panagiotoglou, Fred | PRJ | - | - |  |  | 
2800 ¦ IDP - TB App Income Verification | Aleksandra | Panagiotoglou, Fred | PRJ | - | - |  |  | 
3291 ¦ Client Level Pricing | Naveed | Sudan, Arpan | PRJ | - | - | N | mMortgage, RPE, EPC, PostEdge, EDH, Lending BI | 
3366 ¦ OSFI MVP8.2 | Ozgur | Sudan, Arpan | PRJ | - | - | N | LCMS, Lending API, DDGS, Forms Management, PSP, TSYS | 
3454 ¦ mMortage to Contact Center | Ozgur | Sudan, Arpan | PRJ | - | - | G | mMortgage, LCMS, DM, DDGS, Lending API, CAAP, Lending BI, CCARS | 
4114 ¦ Digital Switch Pre-Qualification | Joy Rosalynn | Sudan, Arpan | PRJ | - | - | Y | mMortgage, DM, LCMS, Lending API, DDGS, ECIF, EPC, Lending BI, EDSF, EDH | 
538 ¦ TABS Replacement - TAO | Ashish | Varga, Ivan | PRJ | - | - | G | TABS | 
16729 ¦ External Pay Out Letter: Enable for eAcceptance (Duplicate of PBPTINTK-3840) | Neha Vineet | Sahni, Rachna | MOP | - | - | N | mMortgage, DDGS, ECM | 
22543 ¦ Remove 30 day look back from Excalibur Panel 651 | Adinarayana Murthy | Sahni, Rachna | MOP | - | - |  | Excalibur | 
23469 ¦ Payout and Discharges | Neha Vineet | Sahni, Rachna | MOP | - | - |  | Excalibur | 
PRB0032179 ¦ Update print flag in DOC_AUDT | Subaleka | Gupta, Suniti | PRB | - | - | N | Target | 
PRB0032288 ¦ Issue with BRUL21314 DM Insurer Choice | Subaleka | Gupta, Suniti | PRB | - | - | N | DM | 
PRB0032533 ¦ DM - BRUL20704 - Deferred Income "Y" Conditional Approve TXM = No | Subaleka | Gupta, Suniti | PRB | - | - | N | DM | 
PRB0032787 ¦ Fix Host Communication Error due to customer mismatch | Subaleka | Gupta, Suniti | PRB | - | - | N | DM | 
PRB0032847 ¦ Excalibur – Multiple payments reversal cuasing huge ineterest outstanding | Subaleka | Gupta, Suniti | PRB | - | - |  | Excalibur | 
PRB0032900 ¦ MVP2 Ingestion Error | Subaleka | Gupta, Suniti | PRB | - | - |  | LCMS | 
2800 ¦ IDP MVP3 CRs | Aleksandra | Panagiotoglou, Fred | MNT | - | - |  | mMortgage, ECM, ENVOY | 
Notes: 3-Apr
PRB0029495 | Document Status on the DDGS LAS UI for the document ‘LAS Personal Loan Annual Confirmation Letter ‘ does not accurately reflect the printing status once the document is printed.
Suniti
PRB
-
-
DDGS

## Slide 32
February 1st Release Project SIT, UAT, & PAT Timelines
 | Name | Impl Date | Phase | START | END | 6-Oct | 10-Oct | 13-Oct | 17-Oct | 20-Oct | 24-Oct | 27-Oct | 31-Oct | 3-Nov | 7-Nov | 10-Nov | 14-Nov | 17-Nov | 21-Nov | 24-Nov | 28-Nov | 1-Dec | 5-Dec | 8-Dec | 12-Dec | 15-Dec | 19-Dec | 22-Dec | 26-Dec | 29-Dec | 2-Jan | 5-Jan | 9-Jan | 12-Jan | 16-Jan | 19-Jan | 23-Jan | 26-Jan | 30-Jan | 1-Feb
538 | 538 ¦ TABS Replacement - TAO | 1-Feb | SIT | 6-Oct-25 | 21-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 24-Nov-25 | 2-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2616 | Renewal Due Diligence MVP3 | 1-Feb | SIT | 20-Oct-25 | 28-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 1-Dec-25 | 26-Dec-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2754 | RAMP2 January 2026 Release | 1-Feb | SIT | 3-Nov-25 | 9-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 3-Nov-25 | 9-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3366 | OSFI MVP8.2 | 1-Feb | SIT | 27-Oct-25 | 26-Dec-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 29-Dec-25 | 23-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3454 | 3454 ¦ mMortage to Contact Center | 1-Feb | SIT | 15-Sep-25 | 28-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 1-Dec-25 | 23-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4114 | 4114 ¦ Digital Switch Pre-Qualification | 1-Feb | SIT | 8-Sep-25 | 21-Nov-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 24-Nov-25 | 9-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
16729 | External Pay Out Letter: Enable for eAcceptance | 1-Feb | SIT | 10-Nov-25 | 5-Dec-25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 8-Dec-25 | 2-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032179 | Update print flag in DOC_AUDT | 1-Feb | SIT | 5-Jan-26 | 9-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 12-Jan-26 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032288 | Issue with BRUL21314 DM Insurer Choice | 1-Feb | SIT | 5-Jan-26 | 9-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 12-Jan-26 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032533 | DM - BRUL20704 - Deferred Income "Y" Conditional Approve TXM = No | 1-Feb | SIT | 5-Jan-26 | 9-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 12-Jan-26 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032787 | Fix Host Communication Error due to customer mismatch | 1-Feb | SIT | 5-Jan-26 | 9-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 12-Jan-26 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032847 | Excalibur – Multiple payments reversal cuasing huge ineterest outstanding | 1-Feb | SIT | 5-Jan-26 | 9-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 12-Jan-26 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PRB0032900 | MVP2 Ingestion Error | 1-Feb | SIT | 5-Jan-26 | 9-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | UAT | 12-Jan-26 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CBPT Applications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CAAP` |  |  |  | 29-Dec-25 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DDGS |  |  |  | 29-Dec-25 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DM/LCMS |  |  |  | 29-Dec-25 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Excalibur |  |  |  | 29-Dec-25 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Lending API |  |  |  | 29-Dec-25 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
RPE |  |  |  | 29-Dec-25 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TABS |  |  |  | 29-Dec-25 | 16-Jan-26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 33: February 1st Release Infrastructure Dependencies
# | Project | Short Description | Apps | Owner | TO CIS # | TO/DXC PM | Target Date | Comments/ Status
1 |  |  |  |  |  |  |  | 

## Slide 34: February 1st Release PIV – Initiatives with PIV
Initiatives Performing PIV |  | 
Initiatives with PIV ON Implementation Day |  | 
Initiatives Performing HC ON Implementation Day |  | 
Initiatives with PIV AFTER Implementation Day |  | 
Intake # | Initiative Name | PM | Change Type | PIV Required | PIV Planning | PIV Test Case Status | PIV Planning ETA | PIV on Imp. Date | Business Health Check on Imp. day | PIV After Imp. Date

## Slide 35: February 1st Release PIV – Initiatives without PIV
Intake # | Initiative Name | PM | Change Type | PIV Required | PIV Planning | PIV Test Case Status | PIV Planning ETA | PIV on Imp. Date | Business Health Check on Imp. day | PIV After Imp. Date
Initiatives without PIV | 17 | 

## Slide 36: February 1st Release Readiness
N | Not Started | G | In Progress/ On Track | Y | May Miss Target Date | R | Will Miss Target End | C | Complete
SCOPE
Project/ MOPS | OR/ Campaigns / Maint. | Incidents/ PRB Records | CCR | Others | Total
23 | 3 | 25 | - | - | 51
Scope | Schedule | Funct. Testing | Env. | Rel. Readiness | Code Freeze | Overall Status
G | G | G | G | G | G | Y
ACTIVITY | DETAILS | TARGET | ETA | %
Design Review | Completed: All Apps | 25 May | 27 Jun | 100%
Code Review | Completed: All Apps | 25 May | 17 Jul | 100%
Diff Report Review (Final) | Completed: All Apps | 22 Jun | 17 Jul | 100%
Infra Readiness Status | 2918 ¦ SFMC Phase 2 Deposit Use Case WS2: Feedhub setup and code deployment Complete | 14 Jul | 14 Jul | 100%
 | 3553 ¦ CRM to M-Mortgage: Enable new end points Complete |  |  | 
ADM External Review | Completed: All Apps | 22 Jun | 17 Jul | 100%
ADM Operational Review | Completed: All Apps | 22 Jun | 27 Jun | 100%
QA Regression and External Review | QA Regression Testing – 4513 / 4513 TC’s QA External Review – 51 / 51 projects | 11 Jul | 11 Jul | 100%
PIV Planning | PIV TC’s Execution in Test Env – Complete PIV Users confirmation – Complete ADM/QC support for PIV – Complete | 11 Jul | 16 Jul | 100%
Impl Readiness | Backout Matrix review – Complete Backout testing scenario walkthrough and Testing – In Progress MIP walkthrough and Sign Off – Complete Change Records and Resource Alignment – In Progress SCM – Complete ACP – Complete OP Docs - Complete | 18 Jul | 18 Jul | 85%
FOCUS
ISSUE
None
KEY INITIATIVES | APPS
3082 ¦ Hopper Group 2 - CA Calculators 3215, 3216, 3297 ¦ HPP CLP Controls 3366 ¦ OSFI MVP 8.2 and 1E 3553 ¦ CRM to M-Mortgage 3624 ¦ RESL - Update to maximum amortization for insured new construction, condo changes 3745 ¦ Project JEDI (Release 1/2 - July) 3750 ¦ C3 - Include Data Elements in Lending BI & EDH 3843, 3686 ¦ RESL MOD POD- July 3907 ¦ F25 Revenue Program 4033 ¦ Hopper 3 & 5 OSFI projects 4102 ¦ Shift Left - MVP1 4105 ¦ Client at Risk | CBPT: 20 Non CBPT: 8

## Slide 37: February 1st Release Project Backout Matrix

## Slide 38: February 1st Release Out of Release Scope
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete
Summary:
None
Open Risks / Issues:
None
Awareness:
None
C​ | T​ | Imp​ | Item​ | PM​ | Type​ | REQ​ | DEV​ | QA​ | Apps​
 |  |  | None |  |  |  |  |  | 
Notes: 3-Apr
PRB0029495 | Document Status on the DDGS LAS UI for the document ‘LAS Personal Loan Annual Confirmation Letter ‘ does not accurately reflect the printing status once the document is printed.
Suniti
PRB
-
-
DDGS

## Slide 39: February 1st Release Projects Backout Testing
Status | Phase | Item

## Slide 40
Application | Tech Lead
February 1st Release ADM Leads (Draft)

## Slide 41
App / Group | PM/Lead | Available 5am-12pm | Changes planned | Contact Name & Phone Number
ECIF Services | Anisah |  |  | a. Mailbox.ECIFBaseEssential@cibc.com / Pager - 416 725 7107 (24*7 Support)​ b. harish1.kumar@cibc.com ¦ 647-270-2619 c. AdeshKumar.Bhati@CIBC.com / Adesh Kumar Bhati, (416-272-3493)
CGMI | Anisah |  |  | Ken Plowman Telephone 416-640-8927 ¦ Cell 416-315-9413 Toll Free 866-414-9109 x 8927 ken.plowman@canadaguaranty.ca
CMHC | Anisah |  |  | On Call: (613) 292-2880
GEMI | Anisah |  |  | Level 1:​​​ productionsupport@sagen.ca Level 2:​​​ Sabri.Madaoui@Sagen.ca ¦ 416-986-7156
TransUnion | Anisah |  |  | servicedesk@transunion.ca ¦ Support Desk: 905-570-1952
Equifax | Anisah |  |  | Support Desk: 1-800-387-9986
TEM | Tina Mallick |  |  | P1, T4, (+91 8697310205
February 1st Release App Availability

## Slide 42: February 1st Outstanding Items
Intake # | Initiative Name | PM | Director | CIRA Status | UAT Status | Gated | Notes
Item | Application/Scope | Status | Notes
Backout testing |  |  | 
ACP |  |  | 
OSI |  |  | 
SCM |  |  | 
Item | Open Risks
Core Banking Release SCR Gate | UAT CIRA
EDTS Tungsten WMF Gate | UAT
Gates:
Projects:
Other Items:

## Slide 43: September COINS, Deposit and Lending Release - Scheduling
Initiative | PM | Apps | Current Imp Date
4149 ¦ NSOD forms Update ( Addendum letter) | Onkar Kang | PCA/SAV | 7-Sep
2754 ¦ RAMP2 MVP1b - Unified Product Shelf | Ifeanyi Okeke | CIBC R.Term, DDGS, Forms Management, KC | 7-Sep
16355 ¦ Bill 72 - COPS Monthly Fixed Fee in QC | Princy Gopalan | COLT, PCA/SAV, STB, EDTS, ECM, ENVOY, COMPASS-AIM, GOW, eBanking | 21-Sep
3366 ¦ MVP8.2 1D | Ozgur Durdu | LCMS | 21-Sep
3745 ¦ Project JEDI (release 2/2 - Sep) | Sidhartha Bishoi | RPE, COLT, PCA/SAV, COINS, FX, CI, DDGS, STB, ECM | 21-Sep
3718 ¦ OSFI MVP5.2 | Jill Craig | Excalibur, CLASS, Lending API, CAAP, PostEdge, COINS (Host Facilities) | 21-Sep
3084 ¦ Hopper 4 | Stephen Priestly | DM, LCMS, Excalibur, CAAP, Lending API, CLASS, mMortgage, TABS, EDH, EDSF, CIW, ECIF, GOW, MI Lending, Lending BI | 21-Sep
16298 ¦ Migrate historical document from FileNet to ECM | Sumit | CLASS, Excalibur, Target, ECM | 21-Sep
The Request: Push Sept COINS Release out 2-weeks
JEDI and Bill C72 require current September Deposit (COINS) Release to target Sept 20-21 weekend to align with project schedules.
JEDI cannot be deployed prior to Sept 21 and Bill 72 has a dependency on JEDI.
Current Release Schedule: Sept 6-7 - COINS & Deposit Release Sept 14 - COINS Mass Sept 20-21 - Lending Release
Options | Impacts
Scenario 1 - No COINS Pilot, All Combined Sept 20-21 - COINS Mass, Deposits, Lending Release | First time w/ COINS as No Pilot First time COINS Mass during a release weekend – requires careful implementation alignment COINS has good history of successful releases with no backouts. Overall risk to the release would be Low. Unexplored: possibility of keeping pilot very short; example Pilot Fri/Sat, Mass Sat/Sun
Scenario 2 - Historically made 2-week shift Sept 20-21 - COINS Pilot & Deposit Release Sept 28 - COINS Mass Oct 4-5 - Lending Release | Lending Release would be required to push out 2-weeks to Oct 4-5 weekend. Test environment for following November release will be impacted. Assessment required on whether this can be absorbed or if release has to push out.
Scenario 3 - CLASS to Implement all OSFI changes in COINS Pilot Sept 20-21 - COINS Pilot, Deposits, CLASS only or all Lending (pending assessment) Sept 27 - COINS Mass Oct 4-5 – Rest of Lending Release (in case necessary) | In this scenario OSFI CLASS changes that would have been split across 2 releases would be combined and go with the first COINS Pilot release. Remainder of the non-GDF changes in Lending release would be implemented 2-weeks later on Oct 4-5 weekend. Test environment for following November release will be impacted. Assessment required on whether this can be absorbed or if release has to push out.
Impacted Scope:
3745 – JEDI
16355 – Bill C72
OSFI MVP 5.2

## Slide 44: September Release Scope
N | Not Started | G | In Progress, On Track | Y | May Miss Target End | R | Will Miss Target End | C | Complete
September Deposit Release – Sep 8 |  |  |  |  |  |  | 
Item | PM | PD | Type | REQ | DEV | QA | Apps
2981 ¦ Open Banking Data Out | Sanjay | Sahni, Rachna | MOP | - | - | N | ENVOY, CLASS, COLT, Excalibur, IPS
September Deposit Release – Sep 21 |  |  |  |  |  |  |  | 
Item | PM | PD | Type | REQ | DEV | QA | Apps | COINS
16355 ¦ Bill 72 - COPS Monthly Fixed Fee in QC | Princy | Panagiotoglou, Fred | PRJ | - | - |  | COLT, PCA/SAV, STB, EDTS, ECM, ENVOY, COMPASS-AIM, GOW, eBanking | 
3718 ¦ OSFI MVP 5.2 Administrative Approvals (Property Changes) | Jill | Sudan, Arpan | PRJ | - | - | N | Excalibur, CLASS, Lending API, CAAP, PostEdge, COINS (Host Facilities) | Yes
3745 ¦ Project JEDI (release 2/2 - Sep) | Sidhartha | Panagiotoglou, Fred | PRJ | - | - | N | RPE, COLT, PCA/SAV, FX, CI, DDGS, STB, ECM, COINS (Host Facilities) | Yes
September Lending Release – Sep 21 |  |  |  |  |  |  | 
Item | PM | PD | Type | REQ | DEV | QA | Apps
2616 ¦ Renewal Due Diligence MVP2 (Phase 2) | Novy | Sudan, Arpan | PRJ | - | - | N | mMortgage, DDGS, Excalibur, Lending API
16302 ¦ Shift Left - MVP2 | Prateek | Sahni, Rachna | PRJ | - | - | N | DM
2979 ¦ Ministerial Loan Guarantee Compliance Issue | Faisal | Sudan, Arpan | PRJ | - | - | N/A | Excalibur, DDGS, ENVOY, CAAP
3084 ¦ Hopper 4 - FHDC Controls | Stephen | Sudan, Arpan | PRJ | - | - | N | DM, LCMS, Excalibur, CAAP, Lending API, CLASS, mMortgage, TABS, EDH, EDSF, CIW, ECIF, GOW, MI Lending, Lending BI
3503 ¦ CIPS Tranche-3 Ph2 | Sudarshi | Panagiotoglou, Fred | PRJ | - | - | N | DDGS, DDGS API
4061 ¦ Fixing Condo Fees for RESL | Ganesh | Sahni, Rachna | MOP | - | - | N | DM
16298 ¦ Migrate historical document from FileNet to ECM | Sumit | Sahni, Rachna | CCR | - | - |  | CLASS, Excalibur, Target, ECM
Notes: 3-Apr
PRB0029495 | Document Status on the DDGS LAS UI for the document ‘LAS Personal Loan Annual Confirmation Letter ‘ does not accurately reflect the printing status once the document is printed.
Suniti
PRB
-
-
DDGS

## Slide 45
Release PIR Recommendations (1/2)
Readiness
&
Code-Freeze
Protection
Release
Status
Meeting
. . .
‘Express’ Exceptions
Process not yet ready to support urgent nature
Project Team forum still the ideal place to obtain necessary approvals.
As needed, issues can be tabled at weekly forum.
Reporting
UAT2 – Defects/Variances
Our PIR discussion can be summarized as having 2 goals:
These process changes aim to support that end.
Testing Timelines
Project Backout Testing
*New*
Release Calendar revision to formally include Backout Testing allocation.
Process Changes to emphasize UAT2 Cycle Defects, and regular reporting in weekly Release Status meeting.
Process Changes to expect early dependency identification and backout planning at project level.

## Slide 46
Release PIR Recommendations (2/2)
UAT2 – Defects/Variances | 
Owner: | QA
Support: | QA, PMO, AD, Business, RM
Change: | For any defects/variances discovered during project UAT2 cycle: Project Team to conduct urgent criticality assessment on the issue. If deemed non-critical, PMs are to facilitate obtaining business approval to defer the variances. If deemed critical, PMs are to facilitate obtaining L9 AD/QA approvals, prior to promoting the fix to testing. QA DSR Report to indicate Red status on any projects with unresolved defects/variances while in project UAT2 cycle.
Reporting | 
Owner: | QA
Change: | For projects in UAT1/2, defect/variances report summaries to be included in weekly Release Status meeting. As an indicator of readiness, and degree of impact to testing, stats to be reported in Release Status meeting detailing concerning Environment Issues and Downtime summary.
Project Backout Testing Planning For any project with changes to >1 app | 
Owner: | QA + PMO
Support: | QA, AD, Business
Change: | After the project-level backout matrix has been finalized, PMs along with QA will be responsible for facilitating the refinement of their overall testing timelines, considering the effort required to test the prioritized backout scenarios.
Testing Timelines For any project with changes to >1 app | 
Owner: | QA
Support: | PMO, AD
Change: | After the SRD has been finalized (or equivalent checkpoint if Agile), QA Managers must ensure their testing timelines include sufficient effort to budget for backout testing, while still protecting a 2-week code freeze.
Readiness
&
Code-Freeze
Protection
Release
Status
Meeting

## Slide 47
Release PIR Recommendations
UAT2 – Defects/Variances | 
Owner: | PMO
Support: | QA, AD, Business, RM
Change: | For any defects/variances discovered during project UAT2 cycle: Project Team to conduct urgent criticality assessment on the issue. If deemed non-critical, PMs are to facilitate obtaining business approval to defer the variances. If deemed critical, PMs are to facilitate obtaining L9 AD/QA approvals, prior to promoting the fix to testing. QA DSR Report to indicate Red status on any projects with unresolved defects/variances while in project UAT2 cycle.
Reporting | 
Owner: | QA
Change: | For projects in UAT1, defect/variances report summaries to be included in weekly Release Status meeting. As an indicator of readiness, and degree of impact to testing, stats to be reported in Release Status meeting detailing concerning Environment Issues and Downtime summary.
Readiness
&
Code-Freeze
Protection
Release
Status
Meeting
. . .
‘Express’ Exceptions
Process not yet ready to support urgent nature
Project Team forum still the ideal place to obtain necessary approvals.
As needed, issues can be tabled at weekly forum.
Phase 1
Reporting
UAT2 – Defects/Variance
Phase 2
Phase 3
Testing Timelines
Project Backout Matrix
Project Backout Testing
PAT Engagement
Phase Gates
Our PIR discussion can be summarized as having 2 goals:
These process changes aim to support that end.
*New*
Phase 1: Immediately / ASAP
Phase 2: Dec 21st
Phase 3: Feb 15th

## Slide 48
Release PIR Recommendations
Readiness
&
Code-Freeze
Protection
Phase 1
Reporting
UAT2 – Defects/Variance
Phase 2
Phase 3
Testing Timelines
Project Backout Matrix
Project Backout Testing
PAT Engagement
Phase Gates
Our PIR discussion can be summarized as having 2 goals:
These process changes aim to support that end.
*New*
Project Backout Matrix For any project with changes to >1 app | 
Owner: | PMO
Support: | AD
Change: | After Solutioning/Design has completed, PMs will be responsible for facilitating the creation of a project-level backout matrix, with the aid of their AD Lead(s). The backout matrix must then be socialized with the project team and Release Management.
Project Backout Testing For any project with changes to >1 app | 
Owner: | PMO
Support: | QA, AD, Business
Change: | After the project-level backout matrix has been finalized, PMs along with QA will be responsible for facilitating the refinement of their overall testing timelines, considering the effort required to test the prioritized backout scenarios.
Testing Timelines For any project with changes to >1 app | 
Owner: | QA
Support: | PMO, AD
Change: | After the SRD has been finalized (or equivalent checkpoint if Agile), QA Managers must ensure their testing timelines include sufficient effort to budget for backout testing, while still protecting a 2-week code freeze.
Phase 1: Immediately / ASAP
Phase 2: Dec 21st
Phase 3: Feb 15th

## Slide 49
Release PIR Recommendations
Readiness
&
Code-Freeze
Protection
Release
Status
Meeting
Phase 1
Reporting
UAT2 – Defects/Variance
Phase 2
Phase 3
Testing Timelines
Project Backout Matrix
Project Backout Testing
PAT Engagement
Phase Gates
Our PIR discussion can be summarized as having 2 goals:
These process changes aim to support that end.
*New*
PAT Engagement For any project with changes to a performance tested app | 
Owner: | PMO
Support: | PAT, QA, AD
Change: | Assess opportunities for early PAT cycles Engage PAT team, detailing specific project changes and target implementation. Obtain tentative PAT start and end dates. Refresh database prior to baseline testing. This activity must be included in overall PAT estimate. PAT Team process education for PMO may be helpful.
Phase Gates | 
Owner: | PMO
Support: | QA, AD, RM
Change: | At key Phase exits (Dev, SIT, UAT), PMs to facilitate a ‘Phase’ Gate within the project team to determine overall readiness to proceed onto next phase, and to provide an indicator of overall readiness toward implementation. Process & Document yet to be defined. RM will support the establishment of the process with inputs from the key teams.
*New*
Phase 1: Immediately / ASAP
Phase 2: Dec 21st
Phase 3: Feb 15th
By adding more formalized internal checkpoints, and increasing our holistic visibility of budding issues, we will be much more likely to be ready and on-time.

## Slide 50
Release PIR Recommendations (1/2)
Project Backout Matrix For any project with changes to >1 app | 
Owner: | PMO
Support: | AD
Change: | After Solutioning/Design has completed, PMs will be responsible for facilitating the creation of a project-level backout matrix, with the aid of their AD Lead(s). The backout matrix must then be socialized with the project team and Release Management.
Project Backout Testing For any project with changes to >1 app | 
Owner: | PMO
Support: | QA, AD, Business
Change: | After the project-level backout matrix has been finalized, PMs along with QA will be responsible for facilitating the refinement of their overall testing timelines, considering the effort required to test the prioritized backout scenarios.
Testing Timelines For any project with changes to >1 app | 
Owner: | QA
Support: | PMO, AD
Change: | After the SRD has been finalized (or equivalent checkpoint if Agile), QA Managers must ensure their testing timelines include sufficient effort to budget for backout testing, while still protecting a 2-week code freeze.
Readiness
&
Code-Freeze
Protection
Release
Status
Meeting
PAT Engagement For any project with changes to a performance tested app | 
Owner: | PMO
Support: | PAT, QA, AD
Change: | Assess opportunities for early PAT cycles Engage PAT team, detailing specific project changes and target implementation. Obtain tentative PAT start and end dates. Refresh database prior to baseline testing. This activity must be included in overall PAT estimate. PAT Team process education for PMO may be helpful.
Any issues with or delays in meeting these process changes will be tabled at the weekly Release meeting.
Our PIR discussion can be summarized as having 2 goals:
Readiness & Code-Freeze Protection
These process changes aim to support that end.

## Slide 51
Release PIR Recommendations (2/2)
UAT2 – Defects/Variances | 
Owner: | PMO
Support: | QA, AD, Business, RM
Change: | For any defects/variances discovered during project UAT2 cycle: Project Team to conduct urgent criticality assessment on the issue. If deemed non-critical, PMs are to facilitate obtaining business approval to defer the variances. If deemed critical, PMs are to facilitate obtaining L9 AD/QA approvals, prior to promoting the fix to testing. QA DSR Report to indicate Red status on any projects with unresolved defects/variances while in project UAT2 cycle.
Reporting | 
Owner: | QA
Change: | For projects in UAT1, defect/variances report summaries to be included in weekly Release Status meeting. As an indicator of readiness, and degree of impact to testing, stats to be reported in Release Status meeting detailing concerning Environment Issues and Downtime summary.
Readiness
&
Code-Freeze
Protection
Release
Status
Meeting
. . .
‘Express’ Exceptions
Process not yet ready to support urgent nature
Project Team forum still the ideal place to obtain necessary approvals.
Phase Gates | 
Owner: | PMO
Support: | QA, AD, RM
Change: | At key Phase exits (Dev, SIT, UAT), PMs to facilitate a ‘Phase’ Gate within the project team to determine overall readiness to proceed onto next phase, and to provide an indicator of overall readiness toward implementation. Process & Document yet to be defined. RM will support the establishment of the process with inputs from the key teams.
*New*
As needed, issues can be tabled at weekly forum.
By adding more formalized internal checkpoints, and increasing our holistic visibility of budding issues, we will be much more likely to be ready and on-time.

## Slide 52: Oct 18th – Remaining Scope
- CIBC CONFIDENTIAL
PBPT-3473: DM CMHC
+ CR04, CR05
PBPT-3509: CRI Remediation
PBPT-3587: DM OR
+ PBPT 3735: DM OR
DM
A
PBPT-1181: Aurora to LCMS
PBPT-1174: OSFI Prefunding
mMTG UI change to support PETENH-103
PETENH-103: New cross sell deposit type
PRB0027662: LCMS Prb for mMTG notification
mMTG
LCMS, Aurora, CAAP, Excalibur
B
No Risks
Dormant/limited pilot
DM Package
Coupled with A2L
Intake # | Initiative Name | Impacted Apps
PBPT 1181 | Aurora to LCMS | Lending BI; Excalibur; LCMS; CAAP; DDGS; AURORA; GOW; Cognos; EFT
PBPT-1174 | OSFI B20 ICR Pre-funding Document Verification Process | LCMS
PBPT-3461, 3024 | mMortgage Enhancements (Story: PETENH-103) | LCMS, mMtg
PRB0027662 | LCMS - MMortgage Status not display the Status as "Approved" and continues to show the previous status of "Submitted/ Conditionally Approved" | LCMS
PBPT-3473 | Amend DM logic for CMHC + CR04, CR05 | DM
PBPT 3509 | CRI Remediation for Issue 8 | DM; Lending BI; EDH
PBPT-3587 | DM table and param changes for October 2020 | DM
PBPT-3735 | DM table and param changes for December 2020 | DM

## Slide 53
Sep 21st Release QA Readiness
KEY ACTIVITIES | DETAIL | STATUS
QA Cross Impact Analysis with ADMs to identify any additional testing scenarios required | QA leads and ADMs conducted release cross impact analysis meeting and result has been shared with ADM and QA teams, this activity is completed | 100%
PIV Test Plan and/or PIV Test Cases Status | PIV Test Plan and Cases execution in progress | 0%
UAT/Testing Exit Sign Offs | UAT Exit sign off in progress | 0%
CBPT Release Regression Testing | CBPT Release Regression Testing is in progress | 99%
Compass Release Regression Testing | Compass Release Regression Testing in progress | 60%
QA Backout Testing – create, review and execute of Backout testing scenarios | QA Backout Testing planning is done, exection from Sept 15-19 | 50%
PAT Testing | PAT Testing in progress | 0%
TEM weekend support for applications and QA machines in test environment(s) | This activity is in progress | 0%

## Slide 54
Application | Tech Lead | ACP Status | OSI / Run Books | SCM
AAM | Botu, Atchyuta Ramarao; Bucur, Alexandre | Draft | Draft | Draft
CI | Botu, Atchyuta Ramarao; Bucur, Alexandre; | Draft | Draft | Draft
CIBC R.Term | Lakkakula, Siribindhu; Varghese, Kithu | Draft | Draft | Draft
CLASS | Singh, Madan; Sahu, Rohit; | Draft | Draft | Draft
CSB | Botu, Atchyuta Ramarao; Cook, David R.; Bucur, Alexandre; | Draft | Draft | Draft
DDGS | Desai, Vini Virendra; Singh, Avtar; Chang, Cher; | Draft | Draft | Draft
Envoy | PALREDDY, DAMODHAR REDDY; Sharma, Rishi Kant; | Draft | Draft | Draft
FX | Botu, Atchyuta Ramarao; Bucur, Alexandre; | Draft | Draft | Draft
IPS | Botu, Atchyuta Ramarao; Bucur, Alexandre; | Draft | Draft | Draft
LAS | Grantham, Ron | Draft | Draft | Draft
LCMS | Panigrahi, Nrusinghnath; Tiwari, Divya; Acharya, Smruti; | Draft | Draft | Draft
PCA/SAV | MacNeil, Natalie | Draft | Draft | Draft
RRIF Printing | Botu, Atchyuta Ramarao; Bucur, Alexandre; | Draft | Draft | Draft
RRSP/TFSA | Botu, Atchyuta Ramarao; Bucur, Alexandre; | Draft | Draft | Draft
SDB | Botu, Atchyuta Ramarao; Bucur, Alexandre; | Draft | Draft | Draft
STB | Foster, Shannon | Draft | Draft | Draft
Sep 21st Release ADM Tracker

## Slide 55
App / Group | PM/Lead | Available 5am-12pm | Changes planned | Contact Name & Phone Number
ECIF Services | Divyanshu |  |  | a. Mailbox.ECIFBaseEssential@cibc.com / Pager - 416 725 7107 (24*7 Support)​ b. harish1.kumar@cibc.com ¦ 647-270-2619 c. AdeshKumar.Bhati@CIBC.com / Adesh Kumar Bhati, (416-272-3493)
CGMI | Divyanshu |  |  | Ken Plowman Telephone 416-640-8927 ¦ Cell 416-315-9413 Toll Free 866-414-9109 x 8927 ken.plowman@canadaguaranty.ca
CMHC | Divyanshu |  |  | On Call: (613) 292-2880
GEMI | Divyanshu |  |  | Level 1:​​​ applicationhotline@sagen.ca Level 2:​​​ Sabri.Madaoui@Sagen.ca
TransUnion | Divyanshu |  |  | servicedesk@transunion.ca ¦ Support Desk: 905-570-1952
Equifax | Divyanshu |  |  | Support Desk: 1-800-387-9986
TEM | Pritesh R. Sahoo |  |  | PA, T4, +91-9035905870
Sep 21st Release App Availability

## Slide 56
Concern | Options | Final Direction
Sep 21st Release - PIR